## Sheet3
Details for time extension
Address:
SN | Details |  |  | Remarks
1 | Name of (Sub) Project
2 | Location
3 | Contract ID / Major work Details
4 | Name of Contractor
5 | Agreement amount(Contract Amount)
6 | Agreement Date
7 | Work Completion date as per Agreement
8 | Work Progress % | Physical | Financial
9 | Contractor's application | Yes/No | date
10 | Details of past time extension | First time Up to…..
Second time Up to…..,
Third time Up to…..
11 | Reasons for current time extension | 1
2
12 | Renewal of Performace Security | 1.Yes/No | validity
2.Issuing Bank
3.Validity date
13 | Insurance | 1.Issuing agency | 2.Validity
14 | Details of Works donetill date.
15 | Proposed date of time extension (Duration)
16 | Revised Work Schedule | Yes/No : yes
17 | Financial Liability ( If any)
18 | Variation Order Details,If any | No.of VOs : |  | Total % :
19 | Major works Remaining to be done.
| Submitted by |  | Checked by